Project Report

Data Warehousing Project

Data Warehousing Team

Organization: Okanagan College

Course: COSC471

Team Members: Alex Anthony, John Cortez, Daemon Lewis, Hayden Nikkel, Jackson Rosco

Year: 2026

# 1. Project Issues

## 1.1 Issue Tracking Mechanism

To ensure project velocity and technical integrity, the team utilized GitHub Issues as the primary tracking mechanism, supplemented by weekly in-class status assessments (Stand-Ups) held every Wednesday.

This dual-layered approach allowed for:

- Real-time Communication: Technical blockers were logged on GitHub as they occurred.

- Accountability: Each issue was assigned to a specific "Lead" responsible for resolution and reporting.

- Risk Mitigation: Weekly assessments provided a formal space to pivot when upstream dependencies (like the Data Collection team's APIs) changed.

## 1.2 Issue Log

The following table tracks the most critical management and technical issues encountered from January through March.

| Issue Description | Assignee | Due |
| --- | --- | --- |
| DW Schema/API Spec Changes | Alex Anthony | February 11 |
| VM Environment Isolation | Alex Anthony | March 4 |
| Database Aggregation Implementation | Hayden Nikkel | March 4 |
| pgBackRest Implementation | Alex Anthony | March 4 |
| DRI Server Transition/Migration | Alex Anthony | March 18 |
| System Testing on DRI Servers | Alex Anthony | March 18 |
| GitHub CI/CD Configuration | Alex Anthony | March 18 |
| Warehouse Visual Schema Diagram | Daemon Lewis John Cortez | March 18 |
| Final Documentation | All Members | March 25 |

# 2. Accomplished Project Work

## 2.1 Summary

The Data Warehouse (DW) team successfully delivered a robust infrastructure capable of ingesting, storing, and backing up financial time-series data for machine learning applications.

Major Deliverables:

- Star Schema Database: Implemented a PostgreSQL 16 database utilizing a Star Schema (Fact Table: fact_model_features) designed for high-performance XGBoost queries.

- FastAPI Ingestion Tier: Created a production-ready API that validates and loads data into the warehouse in real-time or batches.

- System Resilience: Configured pgBackRest for automated daily incremental backups and WAL archiving.

- Enterprise Infrastructure: Migrated the entire stack from a local school VM to the Digital Research Alliance of Canada (DRI) servers and implemented GitHub CI/CD for automated testing and deployment.

## 2.2. Finished Tasks by Team Member

Alex Anthony (Product Owner)

- Infrastructure: Engineered the Oracle Linux 8 VM environments (Prod/Test/Dev) and led the final migration to DRI servers.

- Database Architecture: Designed the primary data warehouse schema, ingestion pipeline, and automated pgBackRest backup systems.

- DevOps: Established GitHub CI/CD workflows to automate system testing and deployment.

Hayden Nikkel (Scrum Master)

- Management: Authored and managed the Software Project Management Plan (SPMP) and baseline documentation.

- Data Logic: Led the research and implementation of database aggregation grain (5-15 minute intervals) to meet BI/ML team requirements.

- Administrative Management: Maintained the administrative records and sprint documentation throughout the project lifecycle.

Jackson Rosco

- API Development: Developed and refined specialized FastAPI endpoints to facilitate seamless data handoffs to the BI/ML team.

- Technical Support: Provided critical technical and research support to Alex during the schema design phase and assisted Hayden in refining the technical requirements for the data aggregation logic.

- Documentation: Contributed to the ongoing maintenance of the project’s technical specifications.

Daemon Lewis

- Strategic Support: Provided research and planning support to Hayden for the SPMP and assisted Alex by documenting technical workflows and researching data warehousing best practices to inform the database architecture.

- Documentation: Contributed to the ongoing maintenance of the project’s technical specifications.

- Project Planning: Played a key role in the initial project plan and the final technical documentation polish.

John Cortez

- Administrative Support: Provided operational support to Hayden by managing project plan updates and supported Alex by organizing research data and documentation for the DRI server migration and VM configuration.

- Design: Co-developed the visual schema diagram and managed the final formatting of the project deliverables.

- Documentation: Contributed to the ongoing maintenance of the project’s technical specifications.

# 3. Workload Information

The team followed a workload model based on the SPMP’s effort allocation of 4–12 hours per team member weekly. While theoretical resource requirements estimated up to 40 hours per week per person during peak development, the table below reflects the actual "Units" (Hours) logged for research, development, and documentation across the six sprints.

## 3.1 Workload Distribution Table

| Team Member | Sprint 1&2 | Sprint 3&4 | Sprint 5&6 | Total |
| --- | --- | --- | --- | --- |
| Alex | 22 | 26 | 24 | 72 |
| Hayden | 24 | 20 | 18 | 62 |
| Jackson | 16 | 20 | 14 | 50 |
| Daemon | 16 | 18 | 20 | 54 |
| John | 16 | 18 | 20 | 54 |

## 3.2 Workload Summary by Category

Technical Lead (Alex): Workload peaked during Sprints 3 and 4 with the setup of Oracle Linux VMs, schema design, and implementation of pgBackRest backups. Final units included the critical DRI server migration and CI/CD setup.

Management & Data Logic (Hayden): Units were heavily front-loaded in Sprints 1 and 2 for the creation of the SPMP and baseline documentation. Later units focused on database aggregation logic and final technical report polishing.

Support & Documentation (Jackson, Daemon, John):

Jackson: Units focused on specialized FastAPI endpoint development for the BI/ML team during Sprints 4 and 5.

Daemon & John: Units were distributed between administrative support for Hayden’s documentation, technical support for Hayden and Alex’s issues, and the design of the visual warehouse schema diagram in Sprints 4 and 5.

Collaborative Tasks: All support members shared the workload for initial requirements research and final system preparation for submission.