# The Project Plan

Contents

I. Introduction	1

II. Project Organisation	1

III. Monitoring and Reporting Mechanism	2

IV. Risk Analysis and Risk Mitigation Plan	2

V. Work Breakdown Structure (WBS)	4

VI. Project Milestones	4

VII. Project Schedule	5

## I. Introduction

The objective of this project plan is to outline the schedule, resource allocation, and risk management strategies for the Data Warehouse component of the financial data pipeline. The primary goal of this phase is to successfully aggregate 5-minute raw financial data ticks into 15-minute intervals with engineered features (SMA, Lags, Overnight Gaps) to support downstream machine learning models. This document details the iterative approach taken, specifically highlighting the architectural pivot required to deploy the solution within the restricted DRAC server environment.

## II. Project Organisation

The project is structured around three core functional teams. This plan focuses specifically on the deliverables and responsibilities of the Data Warehouse (DW) Team.

- Stakeholders:

  - Gaetan Hans: Industrial Client

  - Youry Khmevlevsky: Professor/Technical Advisor.

- Data Collection (DC) Team: Responsible for sourcing raw data from APIs (e.g., Financial Modeling Prep), cleaning, validating, and delivering it to the staging environment.

- Data Warehouse (DW) Team: Responsible for database administration, staging architecture, data transformation, continuous loop process management, and data presentation to ML team.

- Machine Learning (ML) Team: The primary internal consumers of the aggregated data warehouse views.

## III. Monitoring and Reporting Mechanism

To ensure alignment despite rapidly changing requirements, the DW team employs a lightweight, Agile communication structure.

- Bi-Weekly Meetings with Client: Conducted every other Tuesday with primary stakeholder. These meetings validate the functional requirements in development.

- Weekly Standups: Conducted every Wednesday with the team. These serve to demonstrate progress, discuss architectural blockers, and approve Change Requests (such as the DRAC migration).

- On-Demand Technical Syncs: Informal coordination with the DC and ML teams to ensure database schema changes (e.g., adding tracking metadata tables) do not break upstream ingestion or downstream model training.

- System Logging: Operational monitoring is handled directly on the DRAC server by tailing the output of the PostgreSQL scripts running within the GNU Screen sessions.

## IV. Risk Analysis and Risk Mitigation Plan

The following table outlines the primary risks encountered and the mitigation strategies employed, heavily influenced by the constraints of the deployment environment.

| Risk ID | Risk Description | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R01 | Infrastructure Constraints: The target DRAC server lacks support for systemd timers and complex Python environments. | High | High | Pivot from a FastAPI/systemd architecture to a pure PostgreSQL script architecture running inside persistent screen sessions. |
| R02 | Data Loss During Ingestion: High-volume 5-minute tick data could be lost during a server restart or database crash. | High | Medium | Implement continuous Write-Ahead Logging (WAL) archiving via pgBackRest with a 5-minute timeout to ensure a minimal data loss. |
| R03 | Process Termination: Background aggregation scripts fail silently after the user disconnects from the SSH session. | High | High | Utilize GNU screen to detach and maintain infinite while loops, keeping the SQL aggregation processes alive independently of user sessions. |
| R04 | Schema Misalignment: Changes to the 15-minute feature calculations break the ML team's predictive models. | Medium | Low | Enforce read-only access for the ML team via designated database views, allowing the DW team to alter underlying tables without breaking front-end queries. |

## V. Work Breakdown Structure (WBS)

The project deliverables are broken down into the following major phases and tasks.

1.0 Initial Architecture (The API Phase)

- 1.1 Configure local development environment and virtual environments.

- 1.2 Develop FastAPI endpoints for data ingestion.

- 1.3 Design SQLAlchemy ORM models for the staging.market_data table.

- 1.4 Implement systemd timers for automated data simulation.

2.0 Database Administration & Backup Strategy

- 2.1 Establish isolated Dev, Test, and Prod databases (cosc471_dev, cosc471_test, cosc471_prod).

- 2.2 Configure database roles and connection privileges.

- 2.3 Deploy pgBackRest stanza for physical backups.

- 2.4 Enable and verify continuous WAL archiving.

3.0 The DRAC Migration (The Pivot)

- 3.1 Deprecate Python API codebase.

- 3.2 Translate data validation logic into raw PostgreSQL constraints.

- 3.3 Develop infinite loop bash/SQL scripts for the Ingestion simulation.

- 3.4 Develop infinite loop bash/SQL scripts for the 15-minute Aggregation.

- 3.5 Deploy scripts to persistent DRAC screen sessions.

## VI. Project Milestones

The project followed an iterative delivery schedule, adapting to infrastructure constraints and professor/client feedback. Below are the key milestones achieved during the development lifecycle.

| Milestone | Description | Target Date | Status |
| --- | --- | --- | --- |
| Infrastructure Provisioning | VM created, PostgreSQL installed, and initial database user roles configured. | Week of Feb 15, 2026 | Completed |
| API & Automation Prototype | FastAPI endpoints deployed for Dev/Test/Prod; systemd timers configured for simulated data ingestion. | Feb 20, 2026 | Completed (Later Deprecated) |
| Backup & Recovery Baseline | Continuous WAL archiving enabled and initial pgBackRest implementation completed. | Feb 23, 2026 | Completed (Later Deprecated) |
| Production Backup Stanzas | pgBackRest stanzas fully configured for automated incremental and full physical backups. | Feb 28, 2026 | Completed (Later Deprecated) |
| DW Schema Initialization | Creation of the core Data Warehouse schema and staging tables. | March 4, 2026 | Completed |
| The "Big Pivot" | Formal approval to deprecate the Python/API stack and transition to a DRAC-native, SQL-only architecture. | March 11, 2026 | Completed |
| DRAC Pipeline Deployment | Infinite loops for simulated ingestion and 15-minute feature aggregation active in persistent screen sessions. | March 18, 2026 | Completed |
| Final Documentation & Delivery | Completion of the Developer's Guide, Configuration Management protocols, and project report. | March 26, 2026 | Completed |

## VII. Project Schedule

The project schedule was initially focused on API and infrastructure development in mid-to-late February.

Phase 1: The API & Automation Sprint (Feb 15 – Feb 28) The team rapidly stood up the three-tier database environment (cosc471_dev, cosc471_test, cosc471_prod). Significant engineering hours were dedicated to resolving service execution errors (e.g., Uvicorn deployment issues) and establishing a resilient backup strategy using pgBackRest stanzas. By the end of February, the system was capable of automated data ingestion and reliable point-in-time recovery.

Phase 2: The Warehouse & Pivot Sprint (March 1 – Present) Early March focused on finalizing the core warehouse schema. However, following the identification of strict DRAC server constraints, the team pivoted on March 11. The schedule was adjusted to accommodate the rewriting of Python-based ingestion and aggregation logic into raw PostgreSQL scripts. This phase prioritized system resilience, resulting in the deployment of background screen sessions to maintain infinite processing loops.