# Change Requests

# I. Change Management Process

During the development lifecycle, changes to the project scope, architecture, and deployment strategy were managed iteratively. Proposed changes were discussed during weekly Wednesday standups with the course professor and industrial client. Approved changes were documented and immediately integrated into the active sprint.

Below are the formalized records of the critical Change Requests (CRs) that shaped the final Data Warehouse architecture.

# II. CR-01: Migration to DRAC Environment (The "Big Pivot")

| Change Request ID | CR-01 | Date Submitted | March 11, 2026 |
| --- | --- | --- | --- |
| Title | Deprecation of Python/FastAPI Stack in favor of DRAC-Native SQL | Status | Approved / Implemented |
| Requester | DW Team | Priority | Critical |
| Description of Change | Abandon the current Python 3.9, FastAPI, and SQLAlchemy ORM architecture. Transition all data ingestion and feature aggregation logic to pure PostgreSQL scripts executable within a restricted DRAC server environment. |  |  |
| Justification | The target DRAC server environment imposes strict limitations on available tooling, restricting the use of complex Python virtual environments, ORMs, and persistent web server processes (Uvicorn). To ensure the pipeline can be handed off and run successfully on the client's infrastructure, the application must be stripped down to raw SQL and bash execution. |  |  |
| Impact Analysis | Technical: Requires a complete rewrite of the data transformation logic from Python/Pydantic into PostgreSQL raw queries. Schedule: Will delay the finalization of the ML feature views by approximately 1-2 weeks while scripts are translated and tested. Resources: Shifts DW team workload entirely to database administration and SQL scripting via vim on the VM. |  |  |
| Backout Plan | Retain the api-server-old directory and the requirements.txt file in version control. If the DRAC migration fails, the team can redeploy the FastAPI application on an alternative, less restrictive Virtual Machine (Arbutus). |  |  |
| Approval Sign-off | Approved verbally during March 11 Weekly Standup. |  |  |

# III. CR-02: Adaptation of Process Automation

| Change Request ID | CR-02 | Date Submitted | March 13, 2026 |
| --- | --- | --- | --- |
| Title | Replacement of systemd Timers with GNU screen Loops | Status | Approved / Implemented |
| Requester | DW Team | Priority | High |
| Description of Change | Replace the previously configured systemd services and timers with infinite while loops running inside detached GNU screen sessions to maintain the ingestion and aggregation processes. |  |  |
| Justification | Following CR-01, it was discovered that the team lacks the required root or sudo privileges to implement persistent systemd daemon services on the DRAC server. To simulate real-time data collection (every 5 minutes) and feature aggregation (every 60 seconds), user-level persistent terminal sessions are required. |  |  |
| Impact Analysis | Technical: High risk of silent failures if a screen session crashes. Requires the creation of an internal tracking mechanism (metadata table) to ensure loops can recover gracefully if restarted. User Experience: Server administrators will need to manually invoke screen sessions to start the pipeline rather than relying on server boot automation. |  |  |
| Backout Plan | None viable on the current DRAC hardware. If screen proves unstable, the team will need to investigate alternative user-space job schedulers like standard cron (if permitted by the environment). |  |  |
| Approval Sign-off | Approved via DW Team consensus. |  |  |

# IV. CR-03: Implementation of Metadata State Tracking

| Change Request ID | CR-03 | Date Submitted | Mid-March, 2026 |
| --- | --- | --- | --- |
| Title | Addition of dw.agg_metadata Table for Process State | Status | Approved / Implemented |
| Requester | DW Team | Priority | Medium |
| Description of Change | Create a new schema table (dw.agg_metadata) utilizing a Key-Value structure to track the last_agg_timestamp and status_flag for the 29 individual symbols being monitored. |  |  |
| Justification | With the transition to infinite background loops (CR-02), the application lost the stateful memory previously provided by the Python API. The aggregation loop needs a persistent, database-native way to know which 15-minute windows have already been processed to avoid recalculating the SMA and Standard Deviation multiple times for the same timeframe. |  |  |
| Impact Analysis | Technical: Adds a minor read/write overhead to the 60-second aggregation loop. Ensures data integrity and idempotency (the loop can be safely restarted without duplicating data). |  |  |
| Backout Plan | Drop the metadata table and rewrite the aggregation SQL to dynamically query the max timeslot from the dw.market_data_15m table on every loop, though this is heavily unoptimized and not desired. |  |  |
| Approval Sign-off | Approved via DW Team consensus. |  |  |

# V. CR-04: Implementation of Multi-Schema Architecture (Star & ML Schemas)

| Change Request ID | CR-04 | Date Submitted | March 26, 2026 |
| --- | --- | --- | --- |
| Title | Implementation of Multi-Schema Architecture (Star & ML Schemas) | Status | Approved / Implemented |
| Requester | DW Team | Priority | Medium |
| Description of Change | Transition from relying on a single, flat data warehouse table (dw.market_data_15m) as the final endpoint, to a decoupled multi-schema architecture. This change introduces a Kimball Star Schema (star schema) utilizing a central fact table and three dimension tables, alongside a dedicated, flattened numerical Feature Store (ml schema). Furthermore, a new "High-Water Mark" routing loop (star_router_loop.sh) is introduced to automate the delta load into the Star Schema. |  |  |
| Justification | The existing flat table structure suffered from disk I/O bottlenecks during massive historical analytical queries (evidenced by 183ms execution times on 3-year sweeps). Furthermore, the downstream consumers have conflicting needs: the ML team requires a purely numeric, one-hot encoded 2D matrix for XGBoost training, while BI/analytical consumers require human-readable dimensions and text strings. Separating these concerns into dedicated schemas optimizes the data specifically for its intended consumer, reducing analytical query times by ~93x (down to <2ms) and eliminating data-wrangling overhead for the ML team. |  |  |
| Impact Analysis | Technical: Requires the creation of star and ml schemas, the one-time seeding of static dimension tables (dim_date, dim_timeslot, dim_symbol), execution of a historical CTAS (Create Table As Select) migration, and the deployment of a new infinite bash loop. Schedule: Minimal. The new architecture can be built and populated in parallel to the live dw pipeline without disrupting ongoing ingestion or 15-minute aggregation loops. Resources: Increases the storage footprint on the DRAC server slightly due to the highly denormalized historical_feature_store in the ml schema, but drastically reduces CPU, Disk I/O, and work_mem load during read operations. |  |  |
| Backout Plan | Terminate the star_router_loop.sh screen session and drop the star and ml schemas. The original dw.market_data_15m table remains fully intact, continuously updated, and functional. Downstream teams can revert their connection strings to point back to the dw schema if the new architecture fails. |  |  |
| Approval Sign-off | Approved via DW Team consensus. |  |  |